## PR59 - CDBG Activities at Risk
U.S. Department of Housing and Urban Development
Office of Community Planning and Development
Integrated Disbursement and Information System
CDBG Activities At Risk Dashboard
Grantee: |  | MACON-BIBB COUNTY
Remediation Plans Rejected by the Field Office: 0 Activity
Awaiting Field Office Review: 1 Activities
Remediation Completed by Grantee but Plan is Still Awaiting Field Office Review: 0 Activity
Awaiting Grantee's Required Explanation and Remediation Plan: 3 Activities
Awaiting Grantee's Completion of Remediation Actions: 5 Activities
Pending At Risk: 4 Activities
X | The activity is currently flagged as At-Risk for the condition specified on the column heading
O | No action required but this activity may soon be flagged as At-Risk for the condition specified on the column heading
^ | The activity review is overdue
Awaiting Field Office Review(1 Activities)
IDIS Activity |  |  | Activity |  |  |  |  | Matrix Code | Remediation Submitted | Remediation Submitted by |  |  | Target Completion Date for Remediation Action | Reason | [5 empty] | Remediation Action |  |  | FO Due Date |  |  |  |  | FO Review Date | Overdue | 1 Year no Draw |  | 3 Year No Acc | 80% Drawn No Acc
3263 |  |  | Central GA Technical College |  |  |  | 0 | 05Z | 2019-06-24 | C90355 |  | 0 | 2019-12-21 | No delay. Activity is proceeding normally. | [5 empty] | When services are complete and a closeout request has been received, the activity will be closed. |  |  | 2019-09-22 |  |  |  | 0 | [5 empty] | X
Awaiting Grantee's Required Explanation and Remediation Plan (3 Activities)
IDIS Activity |  |  |  |  | Activity | [8 empty] | Year |  |  |  | Remediation Plan Submission Deadline |  |  | National Objective |  | Matrix Code |  |  | Fund Date |  |  | Overdue | 1 Year no Draw |  | 3 Year No Acc | 80% Drawn No Acc
3238 |  |  |  | 0 | Scott Mitchell d/b/a Travis Jean Emporium | [8 empty] | 2016 |  |  | 0 | 2019-09-23 |  |  | LMJ |  | 18C |  | 0 | 2018-06-25 15:16 |  |  |  | X
3333 |  |  |  | 0 | 3435 Warpath Road | [8 empty] | 2018 |  |  | 0 | 2019-09-19 |  |  | LMH |  | 14A |  | 0 | 2019-05-28 16:36 | [6 empty] | X
3214 |  |  |  | 0 | Victor Hunt dba Victor's Coat of Many Colors | [8 empty] | 2016 |  |  | 0 | 2019-08-30 |  |  | LMJ |  | 18C |  | 0 | 2018-01-03 11:07 |  |  |  | X
Awaiting Grantee's Completion of Remediation Actions (5 Activities)
IDIS Activity |  |  |  |  | Activity |  |  |  | Matrix Code |  | Fund Date |  | Remediation Submitted |  |  | Remediation Submitted by |  |  | Field Office Approved by |  |  | Field Office Approved On | Target Completion Date for Remediation Action |  |  |  | Actual Completion Date of Remediation Action |  | Overdue | 1 Year no Draw |  | 3 Year No Acc | 80% Drawn No Acc
3255 |  |  |  | 0 | Family Counseling Center |  |  |  | 05Z | 0 | 2018-12-13 09:15 |  | 2019-03-25 |  | 0 | C90355 |  |  | H45167 |  |  | 2019-05-16 | 2019-06-30 | [9 empty] | X
3257 |  |  |  | 0 | HomeFirst |  |  |  | 05U | 0 | 2018-12-13 09:17 |  | 2019-03-25 |  | 0 | C90355 |  |  | H45167 |  |  | 2019-05-16 | 2019-06-30 | [9 empty] | X
3261 |  |  |  | 0 | Macon Volunteer Clinic - Dental |  |  |  | 05M | 0 | 2018-12-13 09:12 |  | 2019-03-25 |  | 0 | C90355 |  |  | H45167 |  |  | 2019-05-16 | 2019-06-30 | [9 empty] | X
3256 |  |  |  | 0 | Loaves & Fishes Ministries |  |  |  | 05Z | 0 | 2018-12-13 09:15 |  | 2019-04-22 |  | 0 | C90355 |  |  | H45167 |  |  | 2019-05-16 | 2019-10-19 | [9 empty] | X
3251 |  |  |  | 0 | Rebuilding Macon - MHR |  |  |  | 14A | 0 | 2018-12-13 09:19 |  | 2019-05-01 |  | 0 | C90355 |  |  | H45167 |  |  | 2019-05-16 | 2019-10-28 | [9 empty] | X
Pending At Risk (4 Activities)
IDIS Activity |  |  |  | Activity | [14 empty] | Year | National Objective |  |  |  | Matrix Code |  |  |  | Fund Date |  | 270 Days no Draw |  | 2 yr 9 Mos No Acc | 66% Drawn No Acc
3221 |  |  |  | Jessica Houston d/b/a Jessica Houston Enterprises | [14 empty] | 2016 | LMJ |  |  |  | 18C |  |  |  | 2018-02-14 12:55 |  | O
3252 |  |  |  | Rebuilding Macon - Volunteer Youth | [14 empty] | 2018 | LMH |  |  |  | 14A |  |  |  | 2018-12-13 09:19 |  |  |  |  | O
3254 |  |  |  | Crisis Line and Safe House | [14 empty] | 2018 | LMC |  |  |  | 05G |  |  |  | 2018-12-13 09:18 |  |  |  |  | O
3258 |  |  |  | Mentors Project | [14 empty] | 2018 | LMC |  |  |  | 05D |  |  |  | 2018-12-13 09:14 |  |  |  |  | O
Report Generated on: 07-01-19. Data from IDIS as of the previous business day. | [30 empty] | Page: |  | 1