## Sheet1
Project Quantity for Package 1 Road List
Road Name | From | To | Miles | Rating | Length | Miles | Width (Ft) | Square Yards | Patchwork,SY, E | Patchwork,SY,A | Price | Cont Amt | Actual Amt | Difference | Deep Patch SY, E | Deep Patch SY, A | Price | Cont Amt | Actual Amt | Difference | Asphalt, Tons 12.5 mm, E | Asphalt,Tons 12.5 mm, A | Price | Cont Amt | Actual Amt | Difference | Asphalt, Tons 9.5 mm, E | Asphalt,Tons 9.5 mm, A | Price | Cont Amt | Actual Amt | Difference | Tack,Gal, E | Tack,Gal, A | Price | Cont Amt | Actual Amt | Difference | Milling,Tons, E | Milling, Tons, A | Price | Cont Amt | Actual Amt | Difference | M.H. (EA), E | M.H. (EA), A | Price | Cont Amt | Actual Amt | Difference | M.H. Risers (EA), E | M.H. Risers (EA), A | Price | Cont Amt | Actual Amt | Difference | W.V. (EA), E | W.V. (EA), A | Price | Cont Amt | Actual Amt | Difference | W.V. Risers (EA), E | W.V. Risers (EA), A | Price | Cont Amt | Actual Amt | Difference | Striping, M (Centerline, Edgeline and Lane Lines) LF, Est | Striping, M (Centerline And Lane Lines), A | Price | Cont Amt | Actual Amt | Difference | Traffic Loop (EA), E | Traffic Loops (EA), A | Price | Cont Amt | Actual Amt | Difference | Painted Arrows(EA), E | Painted Arrows (EA), A | Price | Cont Amt | Actual Amt | Difference | Bike Symbols(EA),E | Bike Symbols(EA),A | Price | Cont Amt | Actual Amt | Difference | Painted Crosswalks(LF), E | Painted Crosswalks (LF), A | Price | Cont Amt | Actual Amt | Difference | Painted Stop Bars(LF), E | Painted Stop Bars(LF), A | Price | Cont Amt | Actual Amt | Difference | RR Symbols(EA), E | RR Symbols(EA), A | Price | Cont Amt | Actual Amt | Difference | Painted Hatching, LF, E | Painted Hatching, LF, A | Price | Cont Amt | Actual Amt | Difference | GABC E | GABC A | Price | Cont Amt | Actual Amt | Difference | RPM, Mile, Est | RPM,M,A | Price | Cont Amt | Actual Amt | Difference | Clip Grass Shoulders, Miles, Est. | Clip Grass Shoulders, Miles, Actual | Price | Cont Amt | Actual Amt | Difference
Fulton Mill Rd | Jane Ann Dr | US 80 | 0.3839 | 61 | 2027 | 0.3839 | 22 | 4954.8889 | 495.4889 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 408.7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297.2933 | 0 | 0 | 0 | 0 | 0 | 408.7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0.3839 | 0 | 0 | 0 | 0 | 0 | 0.7678 | 0 | 0 | 0 | 0 | 0
Fulton Mill Rd | US 80 | Hunnicutt Rd | 1.7095 | 61 | 9026 | 1.7095 | 22 | 22063.5556 | 2206.3556 | [11 empty] | 1820.2433 | [11 empty] | 1323.8133 | [5 empty] | 1820.2433 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 36104 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1.7095 | [5 empty] | 3.4189
Fulton Mill Rd | Western Cir | Bethel Church Rd | 1.0481 | 58 | 5534 | 1.0481 | 22 | 13527.5556 | 1352.7556 | [11 empty] | 1116.0233 | [11 empty] | 811.6533 | [5 empty] | 1116.0233 | [5 empty] | 11 | [5 empty] | 11 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 22136 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 14 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1.0481 | [5 empty] | 2.0962
Fulton Mill Rd | Michael Dr | Skyhawk Cir | 0.21534 | 66 | 1137 | 0.21534 | 22 | 2779.3333 | 277.9333 | [11 empty] | 229.295 | [11 empty] | 166.76 | [5 empty] | 229.295 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 2 | [5 empty] | 2 | [5 empty] | 4548 | [5 empty] | 0 | [5 empty] | 3 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 340 | [11 empty] | 0.21534 | [5 empty] | 0.43068
Dixon Rd | Bethel Church Rd | Rogers Rd | 1.4163 | 60 | 7478 | 1.4163 | 22 | 18279.5556 | 1827.9556 | [11 empty] | 1508.0633 | [11 empty] | 1096.7733 | [5 empty] | 1508.0633 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 29912 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 14 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1.4163 | [5 empty] | 2.8326
Dixon Rd | Fulton Mill | Pine Bloom Pl | 1.2261 | 50 | 6474 | 1.2261 | 22 | 15825.3333 | 1582.5333 | [11 empty] | 1305.59 | [11 empty] | 949.52 | [5 empty] | 1305.59 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 25896 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 14 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1.2261 | [5 empty] | 2.4523
Rogers Rd | Dixon Rd | Fulton Mill | 3.5299 | 59 | 18638 | 3.5299 | 22 | 45559.5556 | 4555.9556 | [11 empty] | 3758.6633 | [11 empty] | 2733.5733 | [5 empty] | 3758.6633 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 8 | [5 empty] | 8 | [5 empty] | 74552 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 14 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 3.5299 | [5 empty] | 7.0598
Total |  |  | 9.5292 |  |  | 9.5292 |  |  | 12298.9778 | [11 empty] | 10146.6567 | [11 empty] | 7379.3867 | [5 empty] | 10146.6567 | [5 empty] | 11 | [5 empty] | 11 | [5 empty] | 12 | [11 empty] | 201256 | [11 empty] | 3 | [17 empty] | 56 | [11 empty] | 340 | [11 empty] | 9.5292 | [5 empty] | 19.0583
Item | Unit | Quantity | Unit Price | Total
Milling | TONS | 10146.6567
Bituminous Tack | GAL | 7379.39
Roadway Patching | SY | 12298.98
12.5 mm Superpave Asphalt | TONS | 10146.6567
9.5 mm Superpave Asphalt | TONS | 0
Install Furnished Sewer Manhole, Storm Manholes, | EA | 11
Install Furnished Water Valve Riser |  | 12
Manhole (Adjustment) | EA | 11
Water Valve (Adjustment) | EA | 12
Traffic Signal Loop Install | EA | 0
Striping (Center Lines, Edge Lines, Lane Lines) | LF | 201256
Painted Arrows | EA | 3
Bike Symbols | EA | 0
Painted Messages | EA | 0
Painted Crosswalks | LF | 0
Painted Stop Bars | LF | 56
Painted RR Symbols | EA | 0
Painted Hatching | LF | 340
Rumble Stripe | SET | 0
RPMs | MILE | 9.53
Clipping Grassed Shoulders | MILE | 19.06