## Sheet1
Project Quantity Sheet for Package 3 Road List
Road Name | From | To |  | Rating | Length | Miles | Width (Ft) | Square Yards | Patchwork,SY, E | Patchwork,SY,A | Price | Cont Amt | Actual Amt | Difference | Deep Patch SY, E | Deep Patch SY, A | Price | Cont Amt | Actual Amt | Difference | Asphalt, Tons 12.5 mm, E | Asphalt,Tons 12.5 mm, A | Price | Cont Amt | Actual Amt | Difference | Asphalt, Tons 9.5 mm, E | Asphalt,Tons 9.5 mm, A | Price | Cont Amt | Actual Amt | Difference | Tack,Gal, E | Tack,Gal, A | Price | Cont Amt | Actual Amt | Difference | Milling,Tons, E | Milling, Tons, A | Price | Cont Amt | Actual Amt | Difference | M.H. (EA), E | M.H. (EA), A | Price | Cont Amt | Actual Amt | Difference | M.H. Risers (EA), E | M.H. Risers (EA), A | Price | Cont Amt | Actual Amt | Difference | W.V. (EA), E | W.V. (EA), A | Price | Cont Amt | Actual Amt | Difference | W.V. Risers (EA), E | W.V. Risers (EA), A | Price | Cont Amt | Actual Amt | Difference | Street Name | Striping, M (Centerline And Lane Lines) LF, E | Striping, M (Centerline And Lane Lines), A | Price | Cont Amt | Actual Amt | Difference | Traffic Loop (EA), E | Traffic Loops (EA), A | Price | Cont Amt | Actual Amt | Difference | Painted Arrows(EA), E | Painted Arrows (EA), A | Price | Cont Amt | Actual Amt | Difference | Bike Symbols(EA),E | Bike Symbols(EA),A | Price | Cont Amt | Actual Amt | Difference | Painted Crosswalks(LF), E | Painted Crosswalks (LF), A | Price | Cont Amt | Actual Amt | Difference | Painted Stop Bars(LF), E | Painted Stop Bars(LF), A | Price | Cont Amt | Actual Amt | Difference | RR Symbols(EA), E | RR Symbols(EA), A | Price | Cont Amt | Actual Amt | Difference | Painted Hatching, LF, E | Painted Hatching, LF, A | Price | Cont Amt | Actual Amt | Difference | GABC E | GABC A | Price | Cont Amt | Actual Amt | Difference | RPM,M,E | RPM,M,A | Price | Cont Amt | Actual Amt | Difference | Clip Grass Shoulders, Miles, Est. | Clip Grass Shoulders, Miles, Actual | Price | Cont Amt | Actual Amt | Difference
Goodall Mill Rd | Jones Rd | Sardis Church Road |  | 44 | 5308 | 1.0053 | 24 | 14154.6667 | 1415.4667 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1167.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849.28 | 0 | 0 | 0 | 0 | 0 | 1167.76 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 |  | 21216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1.0053 | 0 | 0 | 0 | 0 | 0 | 2.02 | 0 | 0 | 0 | 0 | 0
Guy Paine Rd | Pio Nono Ave | MLK |  | 60 | 2761 | 0.52292 | 38 | 11657.5556 | 1165.7556 | [11 empty] | 961.7483 | [11 empty] | 699.4533 | [5 empty] | 961.7483 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 7 | [5 empty] | 7 | [6 empty] | 12354 | [5 empty] | 7 | [5 empty] | 6 | [5 empty] | 0 | [5 empty] | 206 | [5 empty] | 84 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.52292 | [5 empty] | 0
Allied Industrial | End of Rd | Mead Rd |  | 33 | 3457 | 0.65473 | 28 | 10755.1111 | 1075.5111 | [11 empty] | 887.2967 | [11 empty] | 645.3067 | [5 empty] | 887.2967 | [5 empty] | 8 | [5 empty] | 8 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.65473 | [5 empty] | 0
Old Gaull City Rd | Allied Industrial | To a Point 212 Ft South of the RR Crossing |  | 39 | 1500 | 0.28409 | 24 | 4000 | 400 | [11 empty] | 330 | [11 empty] | 240 | [5 empty] | 330 | [5 empty] | 4 | [5 empty] | 4 | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.28409 | [5 empty] | 0.56
Allen Rd | Houston Rd | Hawkinsville Rd |  | 51 | 5780 | 1.0947 | 24 | 15413.3333 | 1541.3333 | [11 empty] | 1271.6 | [11 empty] | 924.8 | [5 empty] | 1271.6 | [5 empty] | 11 | [5 empty] | 11 | [5 empty] | 4 | [5 empty] | 4 | [6 empty] | 23266 | [5 empty] | 2 | [5 empty] | 4 | [5 empty] | 0 | [5 empty] | 68 | [5 empty] | 54 | [5 empty] | 2 | [5 empty] | 40 | [11 empty] | 1.0947 | [5 empty] | 2.18
Allen Rd | Hawkinsville Rd | Eastof 2104 Allen Rd |  | 51 | 1736 | 0.32879 | 22 | 4243.5556 | 424.3556 | [11 empty] | 350.0933 | [11 empty] | 254.6133 | [5 empty] | 350.0933 | [5 empty] | 4 | [5 empty] | 4 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 3472 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.32879 | [5 empty] | 0.66
General Winship | Pinecrest Rd | General Winship Dr S |  | 39 | 1525 | 0.28883 | 22 | 3727.7778 | 372.7778 | [11 empty] | 307.5417 | [11 empty] | 223.6667 | [5 empty] | 307.5417 | [5 empty] | 10 | [5 empty] | 10 | [5 empty] | 2 | [5 empty] | 2 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.28883 | [5 empty] | 0
General Winship South | General Winship | Ingleside Ave. |  | 38 | 748 | 0.14167 | 22 | 1828.4444 | 182.8444 | [11 empty] | 150.8467 | [11 empty] | 109.7067 | [5 empty] | 150.8467 | [5 empty] | 5 | [5 empty] | 5 | [5 empty] | 2 | [5 empty] | 2 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.14167 | [5 empty] | 0
Pinecrest Rd | Old Holton Rd | Elmridge Dr |  | 38 | 2139 | 0.40511 | 22 | 5228.6667 | 522.8667 | [11 empty] | 431.365 | [11 empty] | 313.72 | [5 empty] | 431.365 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 6 | [5 empty] | 6 | [6 empty] | 4278 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.40511 | [5 empty] | 0
Rogers Dr | End of Drive | Kingsley Dr |  | 36 | 1157 | 0.21913 | 22 | 2828.2222 | 282.8222 | [11 empty] | 233.3283 | [11 empty] | 169.6933 | [5 empty] | 233.3283 | [5 empty] | 4 | [5 empty] | 4 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 2314 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.21913 | [5 empty] | 0
Corbin Ave | Riverside Dr | Old Holton Rd |  | 50 | 2547 | 0.48239 | 22 | 6226 | 622.6 | [11 empty] | 513.645 | [11 empty] | 373.56 | [5 empty] | 513.645 | [5 empty] | 7 | [5 empty] | 7 | [5 empty] | 12 | [5 empty] | 12 | [6 empty] | 10188 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 24 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.48239 | [5 empty] | 0.48
Old Holton Rd | Pierce Ave | Corbin Ave |  | 60 | 2344 | 0.44394 | 22 | 5729.7778 | 572.9778 | [11 empty] | 472.7067 | [11 empty] | 343.7867 | [5 empty] | 472.7067 | [5 empty] | 9 | [5 empty] | 9 | [5 empty] | 9 | [5 empty] | 9 | [6 empty] | 9376 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 24 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.44394 | [5 empty] | 0
Thurmond Dr | Nancelon Cir N | Old Holton Rd |  | 34 | 1396 | 0.26439 | 22 | 3412.4444 | 341.2444 | [11 empty] | 281.5267 | [11 empty] | 204.7467 | [5 empty] | 281.5267 | [5 empty] | 5 | [5 empty] | 5 | [5 empty] | 8 | [5 empty] | 8 | [6 empty] | 5584 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 14 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.26439 | [5 empty] | 0
Newton Pl | End of Rd | Thurmond Dr |  | 31 | 225 | 0.042614 | 22 | 550 | 55 | [11 empty] | 45.375 | [11 empty] | 33 | [5 empty] | 45.375 | [5 empty] | 2 | [5 empty] | 2 | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.042614 | [5 empty] | 0
Kingsley Dr | Walton Pl | Rockbridge Rd |  | 52 | 450 | 0.085227 | 22 | 1100 | 110 | [11 empty] | 90.75 | [11 empty] | 66 | [5 empty] | 90.75 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 900 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.085227 | [5 empty] | 0
Rockbridge Rd | Adrian Pl | Kingsley Dr |  | 36 | 539 | 0.10208 | 22 | 1317.5556 | 131.7556 | [11 empty] | 108.6983 | [11 empty] | 79.0533 | [5 empty] | 108.6983 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.10208 | [5 empty] | 0.1
Adrian Pl | Motes Pl | End of Rd |  | 37 | 1326 | 0.25114 | 22 | 3241.3333 | 324.1333 | [11 empty] | 267.41 | [11 empty] | 194.48 | [5 empty] | 267.41 | [5 empty] | 6 | [5 empty] | 6 | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 24 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.25114 | [5 empty] | 0
Walton Pl | Adrian Pl | Motes Pl |  | 29 | 275 | 0.052083 | 22 | 672.2222 | 67.2222 | [11 empty] | 55.4583 | [11 empty] | 40.3333 | [5 empty] | 55.4583 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 12 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.052083 | [5 empty] | 0
Motes Pl | End of Rd | Walton Pl |  | 32 | 976 | 0.18485 | 22 | 2385.7778 | 238.5778 | [11 empty] | 196.8267 | [11 empty] | 143.1467 | [5 empty] | 196.8267 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 0.18485 | [5 empty] | 0
[9 empty] | 9847.2444 | [11 empty] | 8123.9767 | [11 empty] | 5908.3467 | [5 empty] | 8123.9767 | [5 empty] | 113 | [5 empty] | 113 | [5 empty] | 79 | [5 empty] | 79 | [6 empty] | 92948 | [5 empty] | 9 | [5 empty] | 10 | [5 empty] | 0 | [5 empty] | 356 | [5 empty] | 320 | [5 empty] | 2 | [5 empty] | 40 | [11 empty] | 6.854 | [5 empty] | 6
0
Item | Unit | Quantity | Unit Price | Total
Milling | TONS | 8124
Bituminous Tack | GAL | 5908.35
Roadway Patching | SY | 9847.24
12.5 mm Superpave Asphalt | TONS | 8124
9.5 mm Superpave Asphalt | TONS | 0
Install Furnished Sewer Manhole, Storm Manholes, | EA | 113
Install Furnished Water Valve Riser | EA | 79
Manhole (Adjustment) | EA | 113
Water Valve (Adjustment) | EA | 79
Traffic Signal Loop Install | EA | 9
Striping (Center Lines, Edge Lines, Lane Lines) | LF | 92948
Painted Arrows | EA | 10
Bike Symbols | EA | 0
Painted Messages | EA | 0
Painted Crosswalks | LF | 356
Painted Stop Bars | LF | 320
Painted RR Symbols | EA | 0
Painted Hatching | LF | 40
Rumble Stripe | SET | 0
RPMs | MILE | 6.85
Clipping Grassed Shoulders | MILE | 6
Road Name | From | To | Miles
Goodall Mill Rd | Jones Rd | Sardis Church Road | 1.0053
Guy Paine Rd | Pio Nono Ave | MLK | 0.52292
Allied Industrial | End of Rd | Mead Rd | 0.65473
Old Gaull City Rd | Allied Industrial | To a Point 212 Ft South of the RR Crossing | 0.28409
Allen Rd | Houston Rd | Hawkinsville Rd | 1.0947
Allen Rd | Hawkinsville Rd | Eastof 2104 Allen Rd | 0.32879
General Winship | Pinecrest Rd | General Winship Dr S | 0.28883
General Winship South | General Winship | Ingleside Ave. | 0.14167
Pinecrest Rd | Old Holton Rd | Elmridge Dr | 0.40511
Rogers Dr | End of Drive | Kingsley Dr | 0.21913
Corbin Ave | Riverside Dr | Old Holton Rd | 0.48239
Old Holton Rd | Pierce Ave | Corbin Ave | 0.44394
Thurmond Dr | Nancelon Cir N | Old Holton Rd | 0.26439
Newton Pl | End of Rd | Thurmond Dr | 0.042614
Kingsley Dr | Walton Pl | Rockbridge Rd | 0.085227
Rockbridge Rd | Adrian Pl | Kingsley Dr | 0.10208
Adrian Pl | Motes Pl | End of Rd | 0.25114
Walton Pl | Adrian Pl | Motes Pl | 0.052083
Motes Pl | End of Rd | Walton Pl | 0.18485
6.854